## Sheet1
| John's Move |  |  | Student Name
Activity # | Activity | Duration (days) | Predecessors | Group
1 | Plan move |  |  | Plan move
2 | Contact Dion and Carlita | 2 |  | Plan move
3 | Host planning lunch | 1 | 2 | Plan move
4 | Develop and distribute schedule | 1 | 3 | Plan move
5 | Make hotel arrangement in Atlanta | 1 | 2 | Plan move
6 | Prepacking |  |  | Prepacking
7 | Gather packing material | 2 | 1 | Prepacking
9 | Contact 3 moving companies & get bids | 5 | 4 | Prepacking
10 | Select company and negotiate price | 1 | 8 | Prepacking
11 | Sign moving van contract | 1 | 9 | Prepacking
12 | Pack small and delicate items | 2 | 4;7 | Prepacking
13 | Packing |  |  | Packing
14 | Confirm Dion's and Carlita's help | 2 | 4;10 | Packing
15 | Pickup donuts and coffee | 1 | 4 | Packing
16 | Pack apartment |  | 7 | Packing
17 | Pack Kitchen | 2 | 7 | Packing
18 | Pack living room | 2 | 7 | Packing
19 | Pack bedroom | 2 | 7 | Packing
20 | Pack remaining items | 2 | 7 | Packing
21 | Moving |  |  | Moving
22 | Supervise moving van company workers | 1 | 4;10;15 | Moving
23 | Take photos of empty apartment | 1 | 21 | Moving
24 | Drive to Atlanta | 1 | 21 | Moving
25 | Unpacking |  |  | Moving
26 | Confirm availability of apartment for moving van | 1 | 4;21 | Moving
27 | Confirm arrival of van | 1 | 21;23 | Moving
28 | Drive to new apartment; arrive one hour before van | 1 | 25 | Moving
29 | Supervise unloading of all items | 1 | 27 | Moving
30 | Confirm arrival & condition of all items | 0 | 28 | Moving
31 | Unpack and assemble necessary items | 3 | 29 | Moving
32 | Project Closeout |  |  | Project Closeout
33 | Pay hotel bills | 1 | 29 | Project Closeout
34 | Send a thank-you email to Dion and Carlita | 0 | 19 | Project Closeout
35 | Pay all moving bills | 1 | 29 | Project Closeout