## Budget
Weeks
|  | 1 |  |  | 2 |  |  | 3 |  |  | 4
|  | BCWS | BCWP | AC | BCWS | BCWP | AC | BCWS | BCWP | AC | BCWS | BCWP | AC
Planning |  | 45
|  |  | 45 | 35
Packing |  | 216.65
|  |  | 117.1 | 119.5 |  | 108.5 | 108.05
Truck | Gasoline | [6 empty] | 45
[9 empty] | 45 | 65
| Rental Fee | [9 empty] | 400
[12 empty] | 400 | 425
|  |  |  | Week 1 |  |  | Week 2 |  |  | Week 3 |  |  | Week 4
Planned Value (PV)
Earned Value (EV)
Actual Cost (AC)
Cost Variance (CV)
Schedule Variance (SV)
Cost Performance Index (CPI)
Schedule Performance Index (SPI)
Estimate to Complete-typical (ETC)
Estimate to complete - atypical (ETC)
Original Budget at Completion (BAC) or total Budgeted Cost of Work Scheduled (BCWS)